## AI-Bot
Task no | Task detail | Remarks | Status | Hr
1 | admin / Users side authentication |  | done | 5
2 | side bar ( Admin Users, Website Users, Bot Prices , Contact Us, Memberships , Bot Api Settings, Payment Api Settings , Payment & Invoices , Support , Faqs, Website Controler { Header , Footer ), ) icon relevant |  | done | 1.5
3 | Dashboards Bi Static |  |  | 8
4 | Admin Users / Webiste users separte listing | pending |  | ¦
5 | dashboard Profile settings on right menu remove other settings |  | done | 5
| Website Users Record check & verify only status can change |  | done | 1
| Bot Prices Verify & map with user site website | delay due to pricing issue | done | 2.5
| Contact Us Verify and conrrection if needed |  | done | 2
| Membership from user site addition and show on listing user wise memberships start end date membership type etc |  | doing | 4
| Bot API Settings form |  |  | 0.5
| Payment Api Settings form |  | doing | 0
| Payment history on admin site upcoming , done , details of payment show in popup |  | doing | 2
| Payment integration on user site |  | doing | 2
| Support module run and correct admin & ser site both |  |  | 8
| Faqs need to verify |  | done | 1
| Webiste controller ( where footer and header things user can update form admin site ) |  |  | 0.5
| Email ( regsitartion , membership , trail end , support , contact us , password reset ) |  |  | 8

## Pencard
Seq No | Module | Task detail | Remarks | Resource | Status | Hr
| Admin | Admin Login Pagae |  | Hamza Waheed | done
| Admin | General Settings |  | Hamza Waheed | done
| Admin | Payment Gateway |  | Hamza Waheed | done
| Admin | Notifications Crud |  | Hamza Waheed | done |  | 2 | user |  | registration
| Admin | Tutorial |  | Hamza Waheed | done |  |  |  |  | payment gayway
| Users | Registration with payment gateway |  | Hamza Waheed | done |  |  |  |  | login
| Users | Login |  | Hamza Waheed | done |  |  |  |  | forget
| Users | Forget |  |  | P1
| Admin | User Listing |  |  | P1
| Admin | Pending Listings with Approval Buttons |  |  | P2 |  | 3 | admin |  | Users |  |  | pending list | block / approve
| Admin | Create Users and send email to pay |  |  | P2 | [7 empty] | User list
| Admin | Transfer User Type |  |  | P2 | [7 empty] | Create user
| Users | Profile Details |  |  | P3 | [7 empty] | Transfer user type
| Users | Password |  |  | P3
| Users | Support , Whatapps , Email open |  |  | P3
| Users | Tutorial views |  |  | P4 |  | 1 | admin |  |  | settings |  | general settings
| Users | Notification View |  |  | P4 | [7 empty] | payment gatway
| Users | PUC Creation | [10 empty] | Notification crud
| Users | PUC LIST | [10 empty] | Tutroial
| Users | Upload if reject
| Admin | PUC list Order
| Admin | PUC Approved or reject from List |  |  |  |  | 4 | user site | ME > |  | Profile details
| Admin | PUC order History | [8 empty] | Password
| Admin | Bulk Upload | [8 empty] | Support | whatsapp , email
| Users | Analytics | [8 empty] | Tutorial
| Users | Wallet Addtion
| Users | Transaction History
| Admin | Wallet Approve payment | [6 empty] | Home> |  | Notifications |  | view all
| Admin | Wallet History
| Admin | Bank Additon & View Delete | [6 empty] | PUC> |  | PUC creations
| System | Email | [8 empty] | PUC list
| System | PDF Writing & some logical Flow | [8 empty] | Upload images
[7 empty] | 5 | Admin |  | PUC listing | Order |  | approved reject
upload pdf
order history
Bulk upload
[7 empty] | 6 | User site |  |  | Analytics
[11 empty] | Wallet |  | avaialble balance
Add amount payment gatway
Transaction history
[7 empty] | 7 | admin |  | Wallet |  |  | Approved payment
History
Add bank
[7 empty] | 8 | Email
[7 empty] | 9 | pdf writing

## Langsum
Seq No | Module | Task detail | Remarks | Resource | Status | Hr
| Admin | Delete all Inquery form |  | zahid | done | 1.5
| Admin | Delete all Tenant form |  | zahid | done | 1
| Admin | Import Inquery form | validation remaining | zahid |  | 3.5
| Admin | Import tenant form | validation remaining | zahid |  | 2.5
| Admin | Get in touch listing & reply | Email pending | zahid |  | 2.5
| Admin | Dashboard Counter |  | zahid | done | 2
| Website | New Design Integrate | little part | zahid |  | 1
| Website | Signature upload image both forms |  | zahid | done | 1
| Admin | left side profile , name theme colors , dashboard counter icons same as per define |  | zahid
|  | Email when create new user |  | zahid
|  | Audit trail two tas listing forms , updated , deleted user name |  | zahid
|  | Overall theme settings buttons , tables , |  | Kanwal
|  | signature border in website forms |  | zahid